## Sum 1
Count : Issue Description | Column Labels
Row Labels | CR | Defect | Support | Enhancement | NA | Grand Total
Completed | 8 | 26 | 25 | 1 | 7 | 67
Under Development | 4 | 2 |  |  |  | 6
Internal Testing |  | 3 |  |  |  | 3
Under Monitoring |  | 8 | 3 |  |  | 11
Pending | 11 |  |  |  |  | 11
Development Testing | 1 |  |  | 2 |  | 3
Ready For Deployment - On Hold | 1 |  |  |  |  | 1
VAPT | 6 |  |  |  |  | 6
Grand Total | 31 | 39 | 28 | 3 | 7 | 108
Surveyor App, check with Sriram
CR ponits needs to be check with Rajendra Sir
Penny Drop code to be moved for deploment
Domain Id change
VAPT
Customer link

## Tracker
# | Screen Name | Issue Description | Priority | Category | Type | Call Number | Call Status | Status | Timeline | Responsible | Efforts in Hours | Remarks | Issue Raised Date | Issue Raised By | Code Review | RCA | Corrective Action | Preventive Action | OLD Remarks
1 |  | As old OPUS claims are also moved to RCS recently, users unable to process the claims in OPUS now and we need to manually move claims to OPUS one by one. | NA | NA | NA | NA | NA | Completed | 2025-01-07 | Rajendra/Shirish |  | one-time activity (dependent on deployment) | [6 empty] | one-time activity (dependent on deployment)
2 |  | The payment approval/rejection entries updated in OPUS are not being sent to RCS real time hence users need to wait for claim closing until entries are updated. | NA | NA | NA | NA | NA | Completed | 2025-01-07 | Rajendra/Shirish
3 |  | Expense payment is showing under LOSS reserve section while raising RFA | NA | NA | NA | NA | NA | Completed |  |  |  | Dependent on 1 | [6 empty] | Dependent on 1
4 |  | Sometime on RFA screen loss section, reserve ,party name details are coming blank. | NA | NA | NA | NA | NA | Completed |  |  |  | Dependent on 1 | [6 empty] | Dependent on 1
5 |  | While raising RFA invoice not uploaded error is coming | NA | NA | NA | NA | NA | Completed | 2024-12-24 | Rakesh |  | Connect with business and close | [6 empty] | Connect with business and close
6 |  | Claim statuses are not getting updated in RCS as per OPUS. | NA | NA | Defect | NA | NA | Completed |  | Rajendra |  | missing functionality | [6 empty] | missing functionality
7 |  | Surveyor appointment, ILA FSR,PSR validations are not working |  |  | Defect | NA |  | Completed | 2025-01-09 | Pratiksha |  | Switched to Penny drop task - 01/07/2025 10-01-2025: Pratiksha will give it for testing 14-01-2025: It was resolved on 10th Jan. | Mahesh | 2025-01-02 | Database configuration changes |  |  |  | Switched to Penny drop task - 01/07/2025 10-01-2025: Pratiksha will give it for testing 14-01-2025: It was resolved on 10th Jan.
8 |  | 4057 product excess validation is not working |  |  | Defect | NA |  | Completed | 2025-01-14 | Pratiksha |  | UAT done, Production deployment pending 10-01-2025: Needed call number for deployment. and code review 14-01-2025: Deployed on 10th Jan. Ui changes | Vandna | [5 empty] | UAT done, Production deployment pending 10-01-2025: Needed call number for deployment. and code review 14-01-2025: Deployed on 10th Jan. Ui changes
9 |  | Surveyor/claim handler are able to modify the claim details in surveyor app for closed claims as well. | 5 |  | CR | 59904631 | Pending For Closure | Completed | 2025-01-17 | Pratiksha / Surendra /Praveen |  | This needs to be started today and close by morning first half 09-01-2025: Pratikhsa to handlle it for database 10-01-2025: Will be complted by today 13-01-2025:Pratiksha will start working on it from today 14-01-2025: Pratiksha will resolve this today 17-01-2025: Testing status is not closed 19-01-2025: Code has been deployed on 17-01-2025 | Vandna | 2025-01-02 |  |  |  |  | This needs to be started today and close by morning first half 09-01-2025: Pratikhsa to handlle it for database 10-01-2025: Will be complted by today 13-01-2025:Pratiksha will start working on it from today 14-01-2025: Pratiksha will resolve this today 17-01-2025: Testing status is not closed 19-01-2025: Code has been deployed on 17-01-2025
10 |  | While updating NEFT document is not getting uploaded hence unable to update NEFT | NA | NA | Defect | NA | NA | Completed | 2025-01-02 | Pratiksha |  | Connect with business and close, opus side issue rakesh mailed to shirsh 08-01-2025: As confirmed by Pratiksha it was opus issue fixed by shirish and working on production | Mahesh | [5 empty] | Connect with business and close, opus side issue rakesh mailed to shirsh 08-01-2025: As confirmed by Pratiksha it was opus issue fixed by shirish and working on production
11 |  | After PID creation the name is not coming full. | NA | NA | NA | NA | NA | Completed | 2024-12-24 | Shirish/Rajendra
47 | Claim Processing interface | New button is required in Claim processing screen to download the policy document available in DMS against the policy | 5 |  | CR | 58766312 | Pending For Prioritization | Pending |  | Kedar |  |  | Vandna | 2025-01-15
13 |  | Cause of loss update issue ( 3 digit products) while closing and assigning the claims. | NA | NA | Defect | NA | NA | Completed | 2025-01-10 | Rajendra |  | 10-01-2025: Needed call number for deployment. Code deployed by Rajendra Sir | Mahesh | 2025-01-02 |  |  |  |  | 10-01-2025: Needed call number for deployment. Code deployed by Rajendra Sir
14 |  | Surveyor fee calculation asking for investigator also.( The fee calculation is mandatory only for principle surveyor category) | NA | NA | NA | NA | NA | Completed | 2024-12-24 | Rakesh |  | need to add validation | [6 empty] | need to add validation
57 | Claim allocation | Policy Occupancy and Nature of Work Field need to add on claim allocation and verification page and check for other pages also | 1 | Opus | CR | 58960286 | Deployed | Completed | 2025-02-13 | Pratiksha / Rajendra |  | 10-02-2025 : Get the confirmation from user regarding this point 11-02-2025: Confirm with BU 12-02-2025: Please confirm the deployment status and fixed at which end 13-02-2025: It's been deployed from Opus side | Vandna | 2025-01-15 | DB Change: form field script, rcs-claim-service , Branch - Latest-uat-code. API URL- /cccp/rcs/claim/api/saveClaimDataDetails ClaimController - saveClaimDataDetails CalcServiceImpl- saveClaimDataDetails ClaimDataDetailEntity- ClaimDataDetailDto API URL - /cccp/rcs/claim/api/fetchClaimDataDetails ClaimController - fetchClaimDataDetails Dto and Entity is updated as per the addition field Addition field and addition field engeering added on claim data entry page for fire addition fild fire and for marine details, loss assesment. | Backend - common, config, rcsclaim UI - LOR Screen , claim data entry page DB Script -
16 |  | Surveyor Appointment issue in RCS (due to delayed response from Opus). | NA | NA | CR | NA | NA | Completed | 2025-01-10 | Rajendra |  | As per the confirmation from shirish, its ready for deployment. Need to confirm deplpoyment date 10-01-2025: Needed call number for deployment. Code deployed by Rajendra Sir | Mahesh | 2025-01-02 |  |  |  |  | As per the confirmation from shirish, its ready for deployment. Need to confirm deplpoyment date 10-01-2025: Needed call number for deployment. Code deployed by Rajendra Sir
17 |  | Surveyor App issues (claims not visible to surveyors). Opus claim is added from surveyor app then it is added in opus but not visible in surveyor id. | 5 | RCS | Defect | 59906572 | Closed | Under Monitoring | 2025-02-12 | Pratiksha / Surendra |  | 10-01-2025: Mahesh to share case number 13-01-2025: Dropped a mail to Mahesh for refenrence number 14-01-2025: sample claims OC-25-2302-4056-00000174 OC-25-2406-4056-00000049 20-01-2025 : Pratiksha to check with Vandna and conclude 23-01-2025: Pratiksha to conclude today 24-01-2025: Opus claim was not pushed into RCS, but sureyor assiged from surveyor app. that case is not visible to appointed surveyor 27-01-2025: Pratiksha take this on priority 30-01-2025: Pratiksha take this on priority 03-02-2025: Old shared claim is closed, Vandna need to share new claim 05-02-2025: Pratiksh to drop mail to vandna for new claim number 06-02-2025: Drop mail to BU 11-02-2025: Confirm with BU or else change the status of the point to Under Monitoring 12-02-2025: As no new cases is given for debuggin so changingin status to Under Monitoring | Vandna | 2025-01-02 |  |  |  |  | 10-01-2025: Mahesh to share case number 13-01-2025: Dropped a mail to Mahesh for refenrence number 14-01-2025: sample claims OC-25-2302-4056-00000174 OC-25-2406-4056-00000049 20-01-2025 : Pratiksha to check with Vandna and conclude 23-01-2025: Pratiksha to conclude today 24-01-2025: Opus claim was not pushed into RCS, but sureyor assiged from surveyor app. that case is not visible to appointed surveyor 27-01-2025: Pratiksha take this on priority
18 |  | RFA posting issue- (Invoice Upload error) Opus side issue- while uploading invoices for investigayor/ Surveyor it is showing kindly upload invoice. | 1 | Opus | Defect |  |  | Under Monitoring | 2025-01-13 |  |  | 10-01-2025: Issue is resolved confirmed by Shirish. It was happenin at the time of posting data from Opus to RCS, coulmn size varying issue | Vandna | 2025-01-02 |  |  |  |  | 10-01-2025: Issue is resolved confirmed by Shirish. It was happenin at the time of posting data from Opus to RCS, coulmn size varying issue
19 |  | RFA posting issue- (payment status issues) | NA | NA | Defect | NA | NA | Completed |  | Rajendra |  | As per the confirmation from shirish, its ready for deployment. Need to confirm deplpoyment date | Mahesh | 2025-01-02 |  |  |  |  | As per the confirmation from shirish, its ready for deployment. Need to confirm deplpoyment date
20 |  | RFA posting issue- (wrong claim type) | 1 | Opus | Defect |  |  | Completed | 2025-01-24 | Rajendra / Shirish / Pratiksha |  | API endpoint provided to shirish(https://extuat.bajajallianz.com/NonMotorClaimsPortalCloud/cpws/fetchpaymentdetails) 13-01-2025: Shirish will discuss with Rajendra Sir and share update by 12:30 14-01-2025: Testing done by user 20-01-2025: Pratiksha to take follow up from Shirisha and update date and remark 21-01-2025: Deployment on 24-01-2025 23-01-2025: to be dployed on Friday 06-02-2025: Surendra Confirmed with Shirish, it is completed by Rajendra sir | Vandna | 2025-01-02 |  |  |  |  | API endpoint provided to shirish(https://extuat.bajajallianz.com/NonMotorClaimsPortalCloud/cpws/fetchpaymentdetails) 13-01-2025: Shirish will discuss with Rajendra Sir and share update by 12:30 14-01-2025: Testing done by user 20-01-2025: Pratiksha to take follow up from Shirisha and update date and remark 21-01-2025: Deployment on 24-01-2025 23-01-2025: to be dployed on Friday
21 |  | RFA posting issue- (surveyor dates for investigator issue) |  |  | Defect | 59904285 | Pending For Closure | Completed | 2025-01-17 | Pratiksha / Surendra / Praveen |  | Surendra and Praveen will complete today 09-01-2025: GIven for UAT to Mahesh yesterday. 10-01-2025: Follow up with Users 14-01-2025: Surendra will show the changes to Mahesh today 17-01-2025: Given to Mahes for internal testing on 14 Jan 19-01-2025: Code has been deployed on 17-01-2025 | Mahesh | 2025-01-02 |  |  |  |  | Surendra and Praveen will complete today 09-01-2025: GIven for UAT to Mahesh yesterday. 10-01-2025: Follow up with Users 14-01-2025: Surendra will show the changes to Mahesh today 17-01-2025: Given to Mahes for internal testing on 14 Jan 19-01-2025: Code has been deployed on 17-01-2025
22 |  | LOR issue – (documents getting uploaded double) |  |  | Defect | 59904297 | Pending For Closure | Completed | 2025-01-17 | Shivshanker |  | 10-01-2025: Needed call number for deployment. and code review 17-01-2025: Testing status is not closed 19-01-2025: Code has been deployed on 17-01-2025 | Mahesh | 2025-01-02 |  |  |  |  | 10-01-2025: Needed call number for deployment. and code review 17-01-2025: Testing status is not closed 19-01-2025: Code has been deployed on 17-01-2025
23 |  | LOR issue – (status getting changed without uploading) |  |  | Defect | 59904297 | Pending For Closure | Completed | 2025-01-17 | Shivshanker |  | 10-01-2025: Needed call number for deployment. and code review 17-01-2025: Testing status is not closed 19-01-2025: Code has been deployed on 17-01-2025 | Mahesh | 2025-01-02 |  |  |  |  | 10-01-2025: Needed call number for deployment. and code review 17-01-2025: Testing status is not closed 19-01-2025: Code has been deployed on 17-01-2025
24 |  | LOR issue – (network busy error) | NA | NA | Defect | NA | NA | Completed | 2025-01-02 | Vandana |  |  |  | 2025-01-02
25 |  | LOR issue – (visibility roles are not working) |  |  | Defect | 59904297 | Pending For Closure | Completed | 2025-01-17 | Pratiksha / Surendra / Praveen |  | Given for UAT to Mahesh on 07th Jan 10-01-2025: Needed call number for deployment. and code review 17-01-2025: Testing status is not closed 19-01-2025: Code has been deployed on 17-01-2025 | Mahesh | 2025-01-02 |  |  |  |  | Given for UAT to Mahesh on 07th Jan 10-01-2025: Needed call number for deployment. and code review 17-01-2025: Testing status is not closed 19-01-2025: Code has been deployed on 17-01-2025
67 | Data Entry,Claim Assessment | Field additions on assessment and data entry page also location based coverage details to be fetched from Policy | 1 | RCS | CR | 58960286 | Deployed | Completed | 2025-02-13 | Pratiksha / Rajendra |  |  | Vandna | 2025-01-15 | DB Change: form field script, rcs-claim-service , Branch - Latest-uat-code. API URL- /cccp/rcs/claim/api/saveClaimDataDetails ClaimController - saveClaimDataDetails CalcServiceImpl- saveClaimDataDetails ClaimDataDetailEntity- ClaimDataDetailDto API URL - /cccp/rcs/claim/api/fetchClaimDataDetails ClaimController - fetchClaimDataDetails Dto and Entity is updated as per the addition field Addition field and addition field engeering added on claim data entry page for fire addition fild fire and for marine details, loss assesment. Added pagination in frontend for showing the coverage details table
27 |  | salvage page reset | NA | NA | Defect | NA | NA | Completed | 2025-01-08 | Pratiksha |  | 09-01-2024: Pratiksh to update the RCA and corrective action | Mahesh | 2025-01-06 |  |  |  |  | 09-01-2024: Pratiksh to update the RCA and corrective action
28 |  | Sometime PHI does not present on reserve page. In RFA page PHI is visible but in claim reserve page and claimant interested parties pages PHI is not visible | 1 | Opus / RCS | Defect | 59906600 | For Level 2 Analysis | Under Monitoring | 2025-01-27 | Pravin / Shirish |  | 10-01-2025: Mahesh to share case number 13-01-2025: Dropped a mail to Mahesh for refenrence number 14-01-2025: Sample claim No: OC-25-2202-2802-00000465 15-01-2025: PHI data not pushed properly. Temporarily fixed by adding entry. 17-01-2025: Data is notflowing from Opus, Shirsh has to check and revert. Speak with Shirish and conclude 20-01-2025: Pravin to with Shirish and conclude 21-01-2025 : Pravin to conclude with Shirsh 24-01-2025 : Call Shirish and update remark here. 27-01-2025: Logs not available in OPUS, When issue arrives then only can able to check | Mahesh | 2025-01-10 |  |  |  |  | 10-01-2025: Mahesh to share case number 13-01-2025: Dropped a mail to Mahesh for refenrence number 14-01-2025: Sample claim No: OC-25-2202-2802-00000465 15-01-2025: PHI data not pushed properly. Temporarily fixed by adding entry. 17-01-2025: Data is notflowing from Opus, Shirsh has to check and revert. Speak with Shirish and conclude 20-01-2025: Pravin to with Shirish and conclude 21-01-2025 : Pravin to conclude with Shirsh 24-01-2025 : Call Shirish and update remark here. 27-01-2025: Logs not available in OPUS, When issue arrives then only can able to check
29 |  | Supplier addition issue ( sometime unable to add supplier in claim, getting message as “error”) | 1 | RCS | Defect | 59906980 | For Level 2 Analysis | Under Monitoring | 2025-01-24 | Pravin |  | 10-01-2025: Mahesh to share case number 13-01-2025: Dropped a mail to Mahesh for refenrence number 14-01-2025: sample data OC-25-2302-4057-00000002 15-01-2025: Need discussion with BU and anil sir 17-01-2025: Suppliers id is duplicate in RCS database. total 38 Id's are there. Take out the list and give to pratiksha and BU for rectification. Just find the root cause for duplication 20-01-2025: Pravin to check with Pratiksha and BU and conclude 23-01-2025: Pravin to close this today 24-01-2025: Pravin is working on it 27-01-2025: It was resolved on last deployment 17th Jan, | Mahesh | 2025-01-10 |  |  |  |  | 10-01-2025: Mahesh to share case number 13-01-2025: Dropped a mail to Mahesh for refenrence number 14-01-2025: sample data OC-25-2302-4057-00000002 15-01-2025: Need discussion with BU and anil sir 17-01-2025: Suppliers id is duplicate in RCS database. total 38 Id's are there. Take out the list and give to pratiksha and BU for rectification. Just find the root cause for duplication 20-01-2025: Pravin to check with Pratiksha and BU and conclude 23-01-2025: Pravin to close this today 24-01-2025: Pravin is working on it 27-01-2025: It was resolved on last deployment 17th Jan,
30 |  | OC-25-1701-4094-00000020 - claim supplier reserve is showing different on RFA page and claim reserve page. (OPUS) | NA | NA | Defect | NA | NA | Completed | 2025-01-13 | Pratiksha / Shirish |  | 13-01-2025: Pratiksha has checked log and discuss with user and reserve should be modified in Opus for that rajendra has asked user to do that using loader functionality. Mahesh has confirmed over mail | Mahesh | 2025-01-10 |  |  |  |  | 13-01-2025: Pratiksha has checked log and discuss with user and reserve should be modified in Opus for that rajendra has asked user to do that using loader functionality. Mahesh has confirmed over mail
35 |  | Product code 4170 configuration |  |  | Support | 59904014 |  | Completed | 2025-01-13 | Pratiksha |  | 14-01-2025: Pratiksha has configured yesterday | Vandna | 2025-01-13 |  |  |  |  | 14-01-2025: Pratiksha has configured yesterday
32 |  | Request for OPUS & RCS Rights - User Inderjeetsingh02@bajajallianz.co.in is unable to login | NA | NA | Defect | NA | NA | Completed | 2025-01-13 | Surendra/ Praveen |  | 13-01-2025: Surendra will close it today 14-01-2025: Confirm with Mahesh and complete the task | Mahesh | 2025-01-10 |  | User ID is case sensitive field,User Id should be in lowercase but it was configured in camelcase | Updated the User ID witl lowercase |  | 13-01-2025: Surendra will close it today 14-01-2025: Confirm with Mahesh and complete the task
33 |  | RFA posting issue- party details are missing party name, party type, reserve etc. is not showing on RFA page | 1 | RCS | Defect | 59904694 | For Level 2 Analysis | Under Monitoring | 2025-01-27 | Shirish |  | 10-01-2025: Mahesh to share case number 13-01-2025: Dropped a mail to Mahesh for refenrence number 14-01-2025: sample data OC-25-9988-4014-00001083 17-01-2025: Testing status is yet to be closed 20-01-2025: Surendra to recheck with Pratiksha and Pravein 24-01-2025: Surendra to check today. 27-01-2025: This issue is happening from opus side due to duplicate version as confirmed by Shirish | Mahesh | 2025-01-10 |  |  |  |  | 10-01-2025: Mahesh to share case number 13-01-2025: Dropped a mail to Mahesh for refenrence number 14-01-2025: sample data OC-25-9988-4014-00001083 17-01-2025: Testing status is yet to be closed 20-01-2025: Surendra to recheck with Pratiksha and Pravein 24-01-2025: Surendra to check today. 27-01-2025: This issue is happening from opus side due to duplicate version as confirmed by Shirish
34 |  | For 3 Digit products getting "Invalid Cause Of Loss" error in RCS while updating deficiency reason | 1 | Opus | Defect | 59907321 | Closed | Completed | 2025-01-24 | Rajendra / Shirish / Pratiksha |  | 14-01-2025: Surendra to check with Shirish and user. This is issue is already completed 17-01-2025: Status is showing as pending for closure 20-01-2025: Pratiksha to take follow up from Shirisha and update date and remark 21-01-2025: Deployment on 24-01-2025 06-02-2025: ITHD call status is closed so completing the task | Mahesh | 2025-01-13 |  |  |  |  | 14-01-2025: Surendra to check with Shirish and user. This is issue is already completed 17-01-2025: Status is showing as pending for closure 20-01-2025: Pratiksha to take follow up from Shirisha and update date and remark 21-01-2025: Deployment on 24-01-2025
71 | Invoice Submission | FW: OC-25-1602-4056-00000051 OG-25-1603-4056-00000885 MR JACKSON KURIAN 18-Jul-24 | NA | RCS | Support | NA | NA | Completed |  | Pravin |  |  | Vandna | 20-02-2025 |  | Supplier duplicate
72 | Loss Assessment and Data Entry | Field additions on assessment and data entry page also location based coverage details to be fetched from Policy | 1 | RCS | CR | 58960286 | Deployed | Completed | 2025-02-13 | Pratiksha / Surendra |  | 21-01-2025: Testing and Demo file creation. Frontend payload changes and backend log save code commented to resolve 500 Error. 22-01-2025: UAT and 2 observation need to fix today 23-01-2025: wILL deploy changes today and sent for retesting 24-01-2025: Pratiksha and Surendra to conclude in the first half 27-01-2024: Dev completed, Tester asked for updated BRD, Mahesh will share the update BRD. 05-02-2025: Surendra to work on it for auto calculation. 06-02-2025: Finding shared by user, pratiksha has to work on it 07-02-2025: 3 issue reported, 2 closed, 1 is pending , sum issured in policy pdf and api mismatch, Need to check from Rajendra 10-02-2025: UAT DB issue. Testing is done from user side.Get the apprval from User 11-02-2025: Confirmation taken from mahesh on mail. Rajendra sir will release call. Need to prepare jar, build and DB Script and code push to gitlab | Mahesh | 2024-07-01 | DB Change: form field script, rcs-claim-service , Branch - Latest-uat-code. API URL- /cccp/rcs/claim/api/saveClaimDataDetails ClaimController - saveClaimDataDetails CalcServiceImpl- saveClaimDataDetails ClaimDataDetailEntity- ClaimDataDetailDto API URL - /cccp/rcs/claim/api/fetchClaimDataDetails ClaimController - fetchClaimDataDetails Dto and Entity is updated as per the addition field Addition field and addition field engeering added on claim data entry page for fire addition fild fire and for marine details, loss assesment. Added pagination in frontend for showing the coverage details table |  |  |  | 21-01-2025: Testing and Demo file creation. Frontend payload changes and backend log save code commented to resolve 500 Error. 22-01-2025: UAT and 2 observation need to fix today 23-01-2025: wILL deploy changes today and sent for retesting 24-01-2025: Pratiksha and Surendra to conclude in the first half 27-01-2024: Dev completed, Tester asked for updated BRD, Mahesh will share the update BRD
37 | ILM push | Mails are not getting triggered to claim handler or to ILM responsible person in case of auto trigger or normal push/rejection. Mail format is shared in IT call. | 5 | Opus | Defect | 59521901 | Closed | Completed | 2025-01-24 | Rajendra / Pravin / Pratiksha |  | 17-01-2025: Assigned to Pravin to check the mail functionlity 20-01-2025: Pravin has checked it , mails are 21-01-2025 : Deployment on 24-01-2025 06-02-2025: As ITHD call is close, marking this completed | Vandna | 2025-01-15 |  |  |  |  | 17-01-2025: Assigned to Pravin to check the mail functionlity 20-01-2025: Pravin has checked it , mails are 21-01-2025 : Deployment on 24-01-2025
74 |  | 58919465 - RCS and Marine portal Claim document and status integration | 2 | Opus / RCS | CR | 58919465 | Considered For Development | Pending |  | Pratiksha
39 | List of Requirement | LOR Page – Need to add Select All / Unselect All Check box on top for easy | 2 | RCS | CR | 59086029 | For Other Uat | Completed | 2025-02-13 | Pratiksha |  | 20-01-2025: Pratiksha will check and reslove by tomorrow 27-01-2025: Pratiksha will work on it today 30-01-2025: Pratiksha will work on it today, Yesterday working on audit call came for rework also was working on production issue 03-02-2025: Pratiksha has completed the development, She needs to test the same on local and UAT server. she will do it today 05-02-2025:Follow up for testing EOD 06-02-2025: User has given testin approval 11-02-2025: Need to prepare jar, build and DB script. | Vandna | 2025-01-15 | rcs-claim-service - branch Lates-uat-code RcsSupplierController - fetchLorDocumentListByClaimant RcsSupplierServiceImpl- fetchLorDocumentListByClaimant API URL - /cccp/rcs/claim/supplier/api/fetchLorDocumentListByClaimant DB Script change , new filed inserted, listodrequirement , data against the checkpoint where data is uploaded is to disabled and select all option is added. Frontend code will be verified by Pratiksha, | UI Changes -HorizontalInputForm.vue |  |  | 20-01-2025: Pratiksha will check and reslove by tomorrow 27-01-2025: Pratiksha will work on it today
40 | Security | VPN – RCS is currently working on internet so need to add VPN security RCS poral is access outside the BAGIC network and VPN. It should only accessible on BAGIC Network and VPN. Customer page should accessible on Open network, NEFT and Document upload page | 5 | RCS | Enhancement | 59533315 | Pending(Customer Side) | Completed | 2025-02-10 | Anil |  | 03-02-2025: RCS portal is available on open network. It should be accessible only in Bagic and VPN network. As confirmed from Vandna there two pages developed inside the RCS portal which need to accessed by customer that's why it is put on open network. Need to enable domain login so that once user left orgnization he should not able to login | Vandna | 2025-01-15
41 | Data Entry | Claim Section details we have to fecth in opus also added on data entry screen( 4094, 4091) | 5 | Opus / RCS | Defect | 58960286 | Considered For Development | Duplicate | 2025-01-24 | Pratiksha / Surendra |  | 21-01-2025 : Need to discuss with vandna 25-01-2025: Need to dicssu with Vandna checked ITHD call status, This is the same point on Pratiksha and Surendra is currently working. Refernece point 73 | Vandna | 2025-01-15 |  |  |  |  | 21-01-2025 : Need to discuss with vandna 25-01-2025: Need to dicssu with Vandna checked ITHD call status, This is the same point on Pratiksha and Surendra is currently working. Refernece point 73
66 | All Page Headers | Policy Start date and Policy end date fields should be added in the header of each page | 2 |  | CR | 59086029 | For Other Uat | Completed | 2025-02-13 | Pratiksha / Pravin |  | 06-02-2025: Dropped a testing mail to user 10-02-2025: Mahesh has given testing approval 11-02-2025: Need to prepare jar, build and DB script. | Vandna | 2025-01-15 | rcs-claim-service branch latest-uat-code API URL - cccp/rcs/claim/api/fetchClaimDetails ClaimController - fetchClaimDetails ClaimServiceImpl-fetchClaimDetails Field configured in db, policy start date and end | common claim header, policy start date and end date DB Script - allocate, claim inbox, claim processing - 6 fileds
26 |  | Penny drop API for NFET auto verifiation | 1 | Opus / RCS | CR | 59061398 | For Deployment | Ready For Deployment | 2025-03-10 | Pratiksha / Ganesh |  | Pratiksh will complete this today 09-01-2024: Backend work done and deployed. Frontend work is going on, will complete it today 10-01-2024: Testing is going on. close it today 13-01-2025: Shirish has done the deployment, now pratiksha and shirish has to check 14-01-2025: Shirish and Pratiksha will check this today. unable to check yeserday beacuse the UAT refresh was not done 15-01-2025: API changes done from opus side. 16-01-2025: Need to discuss functunality 17-01-2025: As checked ITHD call status, this point is under Internal Testing 20-01-2025: Functional changes arises, Shirsh to update in Opus and then Pratiksha 21-01-2025: Functional changes arises, Shirsh to update in Opus and then Pratiksha 23-01-2025: Changes has been made from Pratiksha side and she will send it for testing today to Mahesh. Also she will share demo file to Rajendra sir for call status update. 24-01-2025: Deployment is pending due to RCS audit call, ILM claim and policy download issue 27-01-2025: Mail triggered to Mahesh for UAT today 30-01-2025: Testing is not completed due to opus upload issue. Pratiksha to follow up with opus team 31-02-2025: Getting null rsponse from opus, dropped a mail to shirish, do follow up again 03--02-2025: Due to opus upload issue unable to move forward for testing. 05-02-2025: Drop mail to shirish for opus upload issue keep me and dilip sir in CC. Once upload issue resolved. need to prepare demo file and share for testing 07-02-2025: Drop a follow up mail to Mahesh 10-02-2025: Got the approval from user on 7th Feb. 11-02-2025: confirmation taken on mail by mahesh. Need to prepare jar and build. Git code push. 28-02-2025: One filed MICR code is not coming from opus side. Pratiksha has to test again 04-03-2025: Please test it today 05-03-2025: Pratiksha will do it today, was busy with non motor 06-03-2025: Pratiksha has to test, as she was busy with non motor and vapt devloment and testing 10-03-2025: Testing will done on production only. Both Opus and RCS deployment required. | Vandna | 2025-01-02 | surveyor-service - branch Latest-uat-code Penny Drop endpoint configuration- opus API VerificationController - saveNeftDetails BatchRestSrviceImpl-saveNeftDetails NeftDetailsEntity- Neft method column added fetchPennyDropStatus-getPennyDropStatus It is one of the method for customers NEFT details verification |  |  |  | Pratiksh will complete this today 09-01-2024: Backend work done and deployed. Frontend work is going on, will complete it today 10-01-2024: Testing is going on. close it today 13-01-2025: Shirish has done the deployment, now pratiksha and shirish has to check 14-01-2025: Shirish and Pratiksha will check this today. unable to check yeserday beacuse the UAT refresh was not done 15-01-2025: API changes done from opus side. 16-01-2025: Need to discuss functunality 17-01-2025: As checked ITHD call status, this point is under Internal Testing 20-01-2025: Functional changes arises, Shirsh to update in Opus and then Pratiksha 21-01-2025: Functional changes arises, Shirsh to update in Opus and then Pratiksha 23-01-2025: Changes has been made from Pratiksha side and she will send it for testing today to Mahesh. Also she will share demo file to Rajendra sir for call status update. 24-01-2025: Deployment is pending due to RCS audit call, ILM claim and policy download issue 27-01-2025: Mail triggered to Mahesh for UAT today
44 | All | Some claims are not being pushed to RCS and hence we need to process them in OPUS- issue started from last week | 1 | Opus | Defect | 59638285 | Deployed | Under Monitoring |  | Shirish / Rajendra |  | 21-01-2025 : Exception report need to analyse 25-02-2025: Deployed On Production By ccadmin on 26th Nov 2024 | Vandna | 2025-01-15 |  |  |  |  | 21-01-2025 : Exception report need to analyse 25-02-2025: Deployed On Production By ccadmin on 26th Nov 2024
45 | All | In some of the claims the insured data does not getting fetched, and we need to manually update the data every time | 2 | Opus / RCS | Defect | 59516520 | Closed | Under Monitoring | 2025-02-06 | Surendra / Shirish |  | 21-01-2025 : Shirish will check log on latest case 24-01-2025: Surendra to check in seconf half. changes deployed on production on 18-oct-2024, comment updated by Rajendra sir against ITHD call 06-02-2025: As ITHD call is closed, changing its status to Under Monitoring | Vandna | 2025-01-15 |  |  |  |  | 21-01-2025 : Shirish will check log on latest case 24-01-2025: Surendra to check in seconf half. changes deployed on production on 18-oct-2024, comment updated by Rajendra sir against ITHD call
55 | Request For Payment | Request For Payment- Type of loss dropdown field for expense payment to be removed - Pratiksha | 2 |  | CR | 59086029 | For Other Uat | VAPT | 2025-03-12 | Pratiksha |  | 17-02-2025: Check first on lower enviornment then it on Production 18-02-2025: Pratiksha will do on 19 20-02-2025: Will do it on friday 24-02-2025: Pratiksha will work on it today 04-03-2025: development walkthourgh given by Pratiksha to vapt team. follow up with VAPT team EOD 05-03-2025: Waiting for VAPT team to revert. get the ITHD call status updated from vandna 06-03-2025: Feedback is pending from VAPT team, Pratiksha needs to do follow up 07-03-2025: Drop update mail on VAPT mail chain 10-03-2025: Feedback not recived from VAPT team, Drop follow up mail EOD 11-03-2025: Follow up with VAPT team for feedback 12-03-2025: Follow up with VAPT team for feedback | Vandna | 2025-01-15
54 | Claim allocation | Claim Allocation Page- Customer mail ID, Contact number, place of loss rows needs to be added on search screen - Pravin/ Check opus api first, if data is comine then we need to add field in RCA side, if data is not coming then we need to ask opus team to send details. Also we need to plan for update of data in older records. | 2 |  | CR | 59086029 | For Other Uat | VAPT | 2025-03-06 | Pravin |  | 17-02-2025: Pravin to work on the analysis part of it. 18-02-2025: Shirish had updated the field in opus API, then after pravin can check. 21-02-2025: Code has been deployed on UAT. As discussed need to update BRD as per the development. Same has to be handled from Maximus side as well. Also check for older records. Need to discus with Rajendra Sir. 24-02-2025: As per Pratiksha's discusstion with Rajendra Sir, changes will be applicable from date of deployment, migration of data is not considered 27-02-2025: Aksed Vandna to update the ITHD call status 04-03-2025: Pratiksha to follow up with VAPT team by EOD | Vandna | 2025-01-15
75 | ALL | Document Service - S3 Bucket Development | 1 | RCS | Enhancement |  |  | Development Testing | 2025-03-18 | Surendra |  | 05-02-2025: Data is getting uploaded on S3 bucke, facing issue while downloading from S3 bucket. Schedular API is still pending. Surendra has to work on one audit call. Pratiksha has shared the issue 06-02-2025: Upload and download working on NEFT, download not working on LOR page. 07-02-2025:LOR changes done on local need to deploy and test again. Damage Item asseement is pending(upload only). check for any upload with pratiksh or user then after you have work on schdular 10-02-2025: Dropped a mail to user for testing . Check with Shirish for opus download issue 12-02-2025: Faces file extention not supported issue ysterday while uploading, get this resolved asap from shirish 13-02-2025: Check uploading from UAT link through old code and schedular program base64 compare and identify. 14-02-2025: Discuss with Sriram, schedular methos should not be in document service. Ask him the other way of calling the schdular through lambda function as API. Also check the base64 issue with him. 17-02-2025: Surendra to check with Sriram, regarding the scheular method through lambda and batch service/ document service, base64 encoding issue 18-02-2025: As confirmed with Surenedra, Unit testing will be done with schedular method only then after implement lambda function. 20-02-2025: Discuss with Sriram, share with me the final time line 24-02-2025: Update the progress of this point by EOD with the final date 27-02-2025: Surendra to check this today and update 04-03-2025: Please check with Sriram 06-03-2025: Files are getting uploaded into S3 Bucket and after upload throu schedular program getting pushed to Opus. Schedular must be handled from lambda function not from document service Also download in not happening due to some opus issue, Check on SIT the upload and download finctionality 07-03-2025: Handle Schdular from Lambda Function 10-03-2025: Sriram suggested to raise SR, but what is purpose of SR, pleae clarrified with Sriram 12-03-2025: SR status is WIP | IT | 2025-01-30
53 | Data Entry | Event code addition option on Data entry screen | 3 |  | CR | 59100964 | Pending For Prioritization | Pending |  | Kedar |  |  | Vandna | 2025-01-15
62 | Data Entry | Provision in RCS to add the action taken by user in claim settlement- FieldAddition ( mandatory while posting RFA after 15 daysof claim registration date ) | 3 |  | CR | 59100964 | Pending For Prioritization | Pending |  | Pratiksha |  |  | Vandna | 2025-01-15
59 | Claim Processing interface | One Time - Claim handler change can be allowed at local level or User Base Explore possibility | 2 |  | CR | 59086029 | For Other Uat | VAPT | 2025-03-06 | Surendra |  | 11-02-2025: Check BRD and Start Development 12-02-2025: chek the development points and share development and unit testing effort 13-02-2025: 2 days effort calculated from Surendra 14-02-2025: Surendr will start today 17-02-2025: Development done, testing pending. Deploy and aks user for testing 18-02-2025: Code deployed on UAT and dropped on UAT for BU testing 20-02-2025: Prepare demo file and follow up fro testing 24-02-2025: Pratiksha will prepare the demo file in 1st half and realeas for internal testing 26-02-2025: Surendra is working on it. will be fixed in one hour and released for BU testing again 27-02-2025: changes has been fixed and asked Vandna to check again 28-02-2025: Asked Vandna to check and revert | Vandna | 2025-01-15 | 07-03-2025: Same upload and download method is used for maximus upload and download, need to handled it with flag confition. Also, the NEFT upload is common, Maximus neft document is uploaded in opus
52 | Claim Reserve | Should not allow local user to update the loss reserve more than 45lakh ( increase and decrease the reserve above or below 45 lakhs) only admin can change | 1 | RCS | CR | 59554524 | For Deployment | Completed | 2025-02-18 | Pratiksha |  | 06-02-2025: Facing issue while appointing surveyor. Pravin wil check with pratiksha 07-02-2025: Pratiksha has complete development, she has to check and update the ITHD call status 10-02-2025: Dropped for Internal Testing to BU on Friday i.e. 7th Feb 11-02-2025: Follow up with BU for testing 12-02-2025: Take testing follow up from BU. 18-02-2025: Confirmation recieved from Vandna | Vandna | 2025-01-15 |  | role - HOCH and amount
49 | Data Entry | Requirement 1 :- Currently for marine policy products 1008 we required child certificates < 1009 product code> while claim regsitration and same needs to fetch in RCS on Claim Processing interface screen This filed is only required for 1008 product claims only | 2 |  | CR | 59415522 | For Other Uat | VAPT | 2025-03-12 | Pratiksha |  | 11-02-2025: Update the progress 17-02-2025: It will go for internal testing today 24-02-2205: Follow up for internal testing and call will go for internal testing as well 04-03-2025: Sriram and Pratiksha has asked for meeting with Cloud team. Follow up for meeting in second half 06-03-2025: VAPT point under development. This will be completed by 7th March 10-03-2025: Drop mail follow up mail EOD 11-03-2025: Follow up and for restesting feedback 12-03-2025: Follow up for VAPT response from VAPT team and testing follow up from BU | Vandna | 2025-01-15
50 | Claim Processing interface | Requirement 2 :- Field Details are not getting fetched for below two fields Field Name Validation 1. Place of Loss it should fetch from opus and keep it editable if user changes it should reflect on other screens too 2. Estimated Amount it should fetch from opus and keep it editable if user changes it should reflect on other screens too | 2 |  | CR | 59415522 | For Other Uat | VAPT | 2025-03-12 | Pratiksha/ Rajendra |  | 11-02-2025: Update the progress 17-02-2025: It will go for internal testing today 20-02-2025: DO the follow up with user 24-02-2205: Follow up for internal testing and call will go for internal testing as well 12-03-2025: Follow up for VAPT response from VAPT team and testing follow up from BU | Vandna | 2025-01-15
38 | Data Entry | Requirement 3 :- Event code autofetchfor opus and Editing option If any user add the event code in opus through loader then it should get added in RCS too and if user changes it in opus / RCS than it should get changed on every screens to Event code should be as per the DOL of claims. if claim loss date does not fall under the event dates then should not allow to add against the claims These dropdown should be fetched from opus or maintain in RCS data base | 1 | Opus / RCS | CR | 59415522 | For Other Uat | VAPT | 2025-03-12 | Pratiksha |  | 20-01-2025: Shirish to check 21-01-2025 : Pratiksha and shirish will check tomorrow 24-01-2025: Data is already coming from opus, check with shirish and coclude it. Prvin to work on it in second half 27-01-2025: Data is not coming from Opus, Check with Shirish 30-01-2025: Pravin has shared details with Shirish to check it from opus 31-01-2025: Pravin to drop mail to shirish for further clarification 03-02-2025: Pravin to check with shirish today and update ny 1:30 04-02-2025: Prvain has checked with Shirish, place of loss is coming on UAT , but need to check on production the same. Pravin to check in the log 05-02-2025: Deployed on UAT, Follow up with BU by EOD for the same 07-02-2025: Coordinat with Vandana for testing, drop follow up mail for UAT 10-02-2025: Got testing confirmation from Mahesh today 11-02-2025: Need to prepare Jar. 24-02-2205: Follow up for internal testing and call will go for internal testing as well 12-03-2025: Follow up for VAPT response from VAPT team and testing follow up from BU | Vandna | 2025-01-15 | rcs-claim -service - Branch - Latest-uat-code API URL - cccp/rcs/claim/api/fetchClaimDataDetails ClaimController - fetchClaimDataDetails ClaimServiceImpl - fetchClaimDataDetails earlier place of loss was set from claimdetailsdto but some time it was coming blank. so picking it from lossdetaildto under claimdetailsdto. so commented additional code |  |  |  | 20-01-2025: Shirish to check 21-01-2025 : Pratiksha and shirish will check tomorrow 24-01-2025: Data is already coming from opus, check with shirish and coclude it. Prvin to work on it in second half 27-01-2025: Data is not coming from Opus, Check with Shirish
46 | Login Page | Domain name need to fetch after first login | 5 | RCS | CR | 59648799 | Assigned | Under Development | 2025-03-20 | Anil |  | 04-02-2025: Updated the Vandna's user id as per the domain id in the uat database but still she can't able to login as her domain user id is not pushed into the keycloak server 05-02-2025: Need to check with the windows team for the same | Vandna | 2025-01-15
60 | Surveyor Appointment | On Surveyor Appointment information page need to add – Surveyor License Expiry Date for information. | 4 |  | CR | 59446970 | Assigned | Pending |  | Pratiksha and Rajendra |  |  | Vandna | 2025-01-15
61 | Claimant Addition | Claimant Addition – While Creation First Select Type of claimant and once created should get added automatically against claim with selected type | 4 |  | CR | 59446970 | Assigned | Pending |  | Kedar |  |  | Vandna | 2025-01-15
64 | Dashboard | Pie Chart for outsatnding Claims on Dashboard | 4 |  | CR | 59446970 | Assigned | Pending |  | Pratiksha |  |  | Vandna | 2025-01-15
58 | RCS | Auto Communication Field multiple E-mail ID entry with ( ; ) separate need to allow so that emails can go to multiple recipients – Agents, Brokers etc. | 4 |  | CR | 59554664 | Assigned | Pending |  | Pratiksha and Dipali |  |  | Vandna | 2025-01-15
76 |  | OC-25-2204-1005-00002686 - Claim not pushed from Opus | 1 | Opus / RCS | Defect | 59998617 | For Level 2 Analysis | Under Monitoring | 2025-02-21 | Surendra / Shirish / Mahesh / Ganesh |  | 07-02-2025: Coordinate and update the issue status 11-02-2025: Rajendra Sir has asked Mahesh to replicate same claim and UAT to reproduce the issue as debugging is not possible in production 12-02-2025: Reproduce the same issue on UAT with help of Mahesh 18-02-2025: Discuss with User and try to reproduce the issue in lower enviorment 20-02-2025: Speak with Mahesh and to replicate the same issue in UAT to test
69 | Claim Approval and Rejection screen | Claim Approval and Rejection screen | 4 |  | CR | 59615262 | Assigned | Pending |  | Rajendra |  |  | Vandna | 2025-01-15
15 |  | Approval Note is not correct in RCS. | 1 | Opus / RCS | CR | 59570465 | Deployed | Ready For Deployment - On Hold | 2025-03-12 | Surendra / Ganesh / Shirish |  | Shirsh to complete the OPUS side API then Surendra has to consume and update same 09-01-2025: Shirsh shared OPUS API yesterday, Surenda to work on it 10-01-2025: Integration done but opus response is incomplete. Opus side development in testing phase will be deployed by today. 14-01-2025: It is under testing from opus side 17-01-2025: As per ITHD call status. It under testing and rework 20-01-2025: Surendra to coordinate with Mahesh for testing closure 21-01-2025: Please take folloe up from Mahesh 23-01-2025: call status for taday was Rework For Technical Reasons. it is pending from opus side. Surendra to work on it today 24-01-2025: UAT cleared from BU, but some changes in Opus side again need to deploy and test. Surendra will in do in second half 27-01-2025: Cod deplpoyed on UAT, DB configuration pending, Surendra will do the testing and afterthat assigned Mahesh for testin 30-01-2025: DB configuration and testing pending from Surendra's end, he will do that today and send for testing. 31-01-2025: got testing from BU yesterday. 05-02-2025: Do the code merging and update 07-02-2025: Code review , code merging has to be done 11-02-2025: Code review has to be done | Vandna | 2025-01-02 |  |  |  |  | Shirsh to complete the OPUS side API then Surendra has to consume and update same 09-01-2025: Shirsh shared OPUS API yesterday, Surenda to work on it 10-01-2025: Integration done but opus response is incomplete. Opus side development in testing phase will be deployed by today. 14-01-2025: It is under testing from opus side 17-01-2025: As per ITHD call status. It under testing and rework 20-01-2025: Surendra to coordinate with Mahesh for testing closure 21-01-2025: Please take folloe up from Mahesh 23-01-2025: call status for taday was Rework For Technical Reasons. it is pending from opus side. Surendra to work on it today 24-01-2025: UAT cleared from BU, but some changes in Opus side again need to deploy and test. Surendra will in do in second half 27-01-2025: Cod deplpoyed on UAT, DB configuration pending, Surendra will do the testing and afterthat assigned Mahesh for testin
65 | Claim allocation | Option to keep the claim in RCS [yes or no] (To bypass the opus motor claims valdiation in RCS for 4095 need to add one field in RCS to select the claim department on allocate screen ) | 5 |  | CR | 59693871 | Assigned | Pending |  | Rajendra |  |  | Vandna | 2025-01-15
51 | Surveyor Workflow - RFA | should ask to update Interim report date while changing the loss reserve and Status Update only for surveyor - not for INV, SVP, Rep or any other | 1 | RCS | Defect | 60062840 | For Level 2 Analysis | Internal Testing | 2025-03-12 | Pravin | 5 | 05-02-2025: Pravin to start working on it. Pravin to share effort for the same 10-02-2025: Started working on it, one point is completed 1 pending 11-02-2025: Under testing. Pravin will test and send for UAT 12-02-2025: Follow up for testing 13-02-2025: UAT done by Mahesh, suggested defienciency resaon should be mandatory. this needs to be handled from backend code. 17-02-2025: Drop follow up mail for testing 21-02-2025: Code deployed, get the testing done from BU and then from Interna Team 26-02-2025: It came for rework, It will be done in next one hour. 27-02-2025: Please check Vandna, issue still persiste. old call number 59904285 28-02-2025: Initial visit date to be added. Ask user to test 04-03-2025: old call number- 59904285, Once testin is approved from BU then we have to change the Call status for QA testing 12-03-2025: Demo file need to be preapare and upload against the ITHD call today only | Vandna | 2025-01-15
12 |  | Surveyor app is not working on mobile. | 5 | RCS | Defect | 59904292 | Closed | Under Development | 2025-03-31 | Pratiksha / Sriram |  | 03-02-2025: Pratiksha has checked the mobilapi version API on production it is returning response. Pratiksha has to discuss same with Sriram 06-03-2025: Pratiksha has sent App API response to sriram for further analysis 07-03-2025: SR for Android tool access for Pratiksha and Saritha will be raised today | Vandna | 2025-01-02 |  |  |  |  | 14-01-2025: Pratiksha to check backend log
42 | Claim Reserve | RCS - Paid amount is not coming in loss reserve screen | 5 | Opus / RCS | Defect | 59915450 | Closed | Completed | 2025-02-17 | Pravin / Pratiksha |  | 21-01-2025 : Will take this point after audit calls 24-01-2025: Surendra to check in seconf half 27-01-2025: Issue coming in Repoen claim, and claims whoes amount is paid 30-01-2025: Surendra to check with Mahesh/ Rajendra and update 31-01-2025: Pravint to check with pratiksha and check in code as well. get tested from BU. 05-02-2025: Deployed on UAT, Follow up with BU by EOD for the same 06-02-2025: Droppes a UAT mail to User 07-02-2025: Follow up for testing 10-02-2025: Follow up for testing 11-02-2025: Mail dropped for UAT 12-02-2025: Follow up with BU for testing 17-02-2025: Testing done, get the mail confirmation from BU | Vandna | 2025-01-15 |  |  |  |  | 21-01-2025 : Will take this point after audit calls 24-01-2025: Surendra to check in seconf half 27-01-2025: Issue coming in Repoen claim, and claims whoes amount is paid
43 | Claim Reserve | while setting reserve it should not allow the amount below paid amount ( outsatnding amount can not be negative). | 5 | Opus / RCS | Defect | 60062840 | For Level 2 Analysis | Internal Testing | 2025-03-11 | Pratiksha |  | 21-01-2025 : Will take this point after audit calls 24-01-2025: Surendra to check in seconf half 27-01-2025: Issue coming in Repoen claim, and claims whoes amount is paid 30-10-2025: Surendra to check with Mahesh/ Rajendra and update 31-01-2025: UI change pratiksha has to work 03-02-2025: Pratiksha has to work on it, please update resolution 05-02-2025: Pratiksha to set the validation after discussion with Surendra 06-02-2025: Dropped a mail to user for testing 07-02-2025: Follow mail up EOD 11-02-2025: Mail dropped for UAT 12-02-2025: Follow up with BU for testing 20-02-2025: Drop mail to Mahesh for testing confirmation 24-02-2205: Follow up for internal testing and call will go for internal testing as well 26-02-2025: Pratiksha will do it in first half only. 27-02-2025: Revert to Vandna 28-02-2025: follow up for testing 04-03-2025: dropped a follow up mail. new call number 60062840 old call number - 59915450 11-03-2025: Prepare demo file , Pratiksha will prepare test cases and check mark report | Vandna | 2025-01-15 | DB Level changes |  |  |  | 21-01-2025 : Will take this point after audit calls 24-01-2025: Surendra to check in seconf half 27-01-2025: Issue coming in Repoen claim, and claims whoes amount is paid
83 |  | Udyam Sewa Portal for MANKIND Group//urgent pls In Udyam Seva portal claim reports are not getting downloaded at insured end | 1 | Opus / RCS | Defect | 60091903 | Closed | Internal Testing | 2025-03-12 | Pratiksha / Surendra |  | 12-02-2025: Surendra checked with Vandna. download was happening. so completing this point. 14-02-2025: Sequence is not prorper. UTR is coming. Pratiksha to check for sequend 17-02-2025: Pratiksh to check from frontend side 18-02-2025: Pratiksha to check this today 20-02-2025 : Pratiksha to check and close by tomorrow 24-02-2025: Pratiksha to check today 27-02-2025: Pratiksha to speak with Vandna and revert to mail. 28-02-2025: Three digit product issue , this is differenet issue need to raise another call for it 04-03-2025: Got approval from Vandna on 28th Feb. old call number - 60010667 needed new call number. 05-03-2025: Get the call number for this development 06-03-2025: Old call number is closed, for raising it for internal and vapt we needed new call number. Old call number - 60010667, new call number 60091903 - Udyam seva serial number sequence issue 07-03-2025: demo file has to prepared and shared for internal testing 10-02-2025: Due to some conflict from Backened side and other team, could able to test the development on UAT. other team is working on it . they will test it today 11-02-2025: Getting proper response from local but not getting response on UAT link, demo, test cases and checkmarks report need to be uploaded 12-03-2025: call status is updated pending for closure as all UI changes were there Surendra has worked with Ganesh to resolve this issue | Vandna | 2025-02-10 |  | sequence wrong in front end on Report screen of UdyamSeva Portal
70 |  | OC-25-1101-6626-00000002 - Unable to select cause of loss for the subjected claim as dropdown is not working | NA | RCS | Defect | NA | NA | Completed | 2025-01-23 | Pravin |  | 20-01-2025: Praveen to check and revert in half an hour 23-01-2025: Update the RCA, corrective action and preventive action | Mahesh | 2025-01-17 |  |  |  |  | 20-01-2025: Praveen to check and revert in half an hour 23-01-2025: Update the RCA, corrective action and preventive action
73 |  | FW: File No. 52768 ## Claim Intimation- D&O_G R Infraprojects Ltd ## Policy no. OG-23-1113-3315-00000121 ## OC-23-1101-3315-00000008 ## WITHOUT PREJUDICE: 220806: Privileged | 1 | RCS | Support |  |  | Completed | 2025-02-13 | Surendra |  | 14-02-2025: Party details updated in database | Mahesh | 2025-02-13 |  | Stake code addition functionality not available to user | Manually data insert in cccp_bagic.parties table | Need to provide Stake code addition functionality to users. Need to defined a process, where BU will share the newly added stake details on weekly basis and we will update those details in RCS
78 | Claimant Addition Page | Unable to Create New Partner ID in RCS | 1 | Opus / RCS | Defect | 59960179 | Closed | Completed | 2025-02-07 | Surendra |  | 30-10-2025: Surendra to check and close this today. 31-01-2025: Do the follow up with Shirish 03-02-2025: Do testing follow up 05-02-2025: Follow up with BU drop mail every EOD 06-02-2025: Code mrging, code review | Mahesh | 2025-01-27 | rcs-claim -service - Branch - Latest-uat-code API URL -/cccp/rcs/claim/parties/api/saveClaimantDetails PartiesController - saveClaimantDetails PartieServiceImpl- saveClaimantDetails PartiesRestServiceImpl - addPartnerDtls Request parameters are modified by the opus team like country filed earlier counrty name was passed but now code is passed but it hardcoded, datOfBirth date format issue
84 |  | Error while changing - Deficiency Reason - OC-25-1302-4056-00000144 |  | RCS | Support |  |  | Completed | 2025-02-20 | Pratiksha / Pravin |  | 20-02-2025: Fixed it from backend | 2025-02-17 | Mahesh |  | Task Number is not updated for subject claim in rcs_claims.task_details . due to duplicate primary key error. task number is generated at the time of claim intimation. | Manually inserted new task number
77 | Search Issue | RCS- Claim Inbox search and download issue | 1 | RCS | Defect | 60062840 | For Level 2 Analysis | Internal Testing | 2025-03-12 | Pravin |  | 30-10-2025: Pravin to work on it once he completed testing on allocate claim 31-01-2025: Pravin to work on it today 03-02-2025: Pravin to work on it today. 04-02-2025: Pravin to work in it today 05-02-2025: Pravin was working on place of loss and estimated loss amount task so couldn't able to work, He will complete this today. 06-02-2025: Development done, local testing going , will deploy today on UAT 07-02-2025: Coordinat with Vandana for testing, drop follow up mail for UAT 10-02-2025: Got testing confirmation from Mahesh today 11-02-2025:Need to prepare jar 27-02-2025: test on UAT. old call number 59960591 28-02-2025: pravin will fix this today test it today 04-03-2025: check with Sriram, 05-03-2025: Pravin discussed with Sriram, he told to try with indexing or else need to increatse the cpu and memory size. 06-03-2025: Pravin to check with Rajendra sir for index creation on db 07-03-2025: After applying indexing on production DB tables claim details, stack details. closed claims are not getting serached. Need to check for CPU and memory option, add date range with maximus feasibility 10-03-2025: It was happening beacuse of pagination issue, Pravin had updated the code , deploy the code on UAT, Prepares test case demo. 11-03-2025: Getting some error while calclating the total count, Pravin will work on it today 12-03-2025: Demo file need to be preapare and upload against the ITHD call today only | Vandna | 2025-01-27 | rcs-claim -service Branch - Latest-uat-code API URL - /cccp/rcs/claim/api/downloadClaimList Entity - ClaimDetailsEntity - claim_details added annotation @BatchSize(size=100) - for loading data in batch instead of one by one. It improves the data fetching perfromance
63 | Claim processing interface | Customer loyalty category, insured rating , loss reserve band, CIBIL Score, risk eveluation, financial health, initial insured profile rating | 3 | Opus / RCS | CR | OP-1223 | Open | Under Development | 2025-03-13 | Pratiksha / Pravin / Ganesh |  | 05-03-2025: Opus side changes going on 06-03-2025: Opus side work done 07-03-2025: Backend work is done from Pravin's side, now Pratiksha has to start the UI part 10-03-2025: Pratiksh to get the field configured in the database today with Pravin. 11-03-2025: Fields configured on backend testing pending 12-03-2025: Pratiksha was testing it yesterday and suppose to prepare the demo file as well. Dev Testing done. file prepared, only need to attach. component and checkmark report is pending | Vandna | 2025-01-15
68 | Loaders - All | Admin part | 5 |  | CR | 59540566 & 59594512 | Assigned | Pending |  | Anil |  |  | Vandna | 2025-01-15
36 | Allocate Claim | Unable to download - on “Allocate Claim Page” unable to download the report | 1 | RCS | Defect | 59960591 | Closed | Completed | 2025-02-13 | Pravin |  | 20-01-2025: Surendra to check it today 23-01-2025: Pravin and me is working on it 24-01-2025: Pravin to check in second half 27-01-2025: Need to check with BU regarding limitaion of date period 30-01-2025: Pravin has written a native qoery when date filter is applied to avoid lazy loading and first reterival 31-01-2025: Ready for UAT deployment. after deployment get tested with BU and get call number for the same 07-02-2025: Coordinat with Vandana for testing, drop follow up mail for UAT 10-02-2025: Got testing confirmation from Mahesh today 11-02-2025:Need to prepare jar | Monika Ranade | 2025-01-14 | rcs-claim -service Branch - Latest-uat-code API URL - /cccp/rcs/claim/api/downloadClaimList ClaimController - downloadClaimList ClaimServiceImpl - downloadClaimList, DownloadClaimDetailsDto, claimEntityToDtos Instead of criteria builder, written native query to fetch the claim details based on location and from and data. then after added new dto to map the fetch records |  |  |  | 20-01-2025: Surendra to check it today 23-01-2025: Pravin and me is working on it 24-01-2025: Pravin to check in second half 27-01-2025: Need to check with BU regarding limitaion of date period
86 | LOR | OP-2042 Default Document List is for RCS claims After claim Generation | 2 | RCS | CR | OP-2042 | Open | Under Development | 2025-03-20 | Pratiksha / Pravin |  | 18-02-2025: We will take this for development on priority. Just to the analysis of changes and imact when we call same method at the time of claim registration | Vandna | 2025-02-17
82 |  | Error while appointing ILM :: Claim No : OC-25-1302-4056-00000143 Date of Loss :07-Feb-2025 - M/S AKRATI OIL MILL | 1 | Opus | Defect | 60015409 | under testing | Completed | 2025-02-14 | Surendra / Ganesh / Shirish |  | 13-02-2025: Code is ready for deployment. 19-02-2025: Opus side change deployed on 14th Feb | Mahesh | 2025-02-07 |  | Opus API - null response "https://bagicnonmotorclm.bajajallianz.com/NonMotorClaimsPortalCloud/cpws/getIlmTriggerDetailsByClaimNumber | Opus code was not deployed in Production
80 | Claim Closure | Claim Closure // Claim no. OC-25-1901-1018-00002019 // MONDELEZ INDIA FOODS PVT LIMITED | NA | Opus / RCS | Defect | NA | NA | Completed | 2025-01-30 | Surendra |  | 31-01-2025: Closed status manually from database through query |  |  |  | Claim is closed in Opus but Open in RCS. Close status is not getting updated in RCS. Opus Issue |  | Need to be fixed from OPUS side
81 | ALL | Document Service - Memory Issue | 1 | RCS | Defect |  |  | Completed | 2025-02-07 | Pratiksha / Pravin |  | 05-02-2025: Drop a mail to opus team, and check till when can be done. Once tested on UAT server same cod has to be merged with Production code 06-02-2025: Pratiksh to coordinate with Pravin to check the download issue 07-02-2025: Pratiksha to coordinate with Dipali and Shivshanker 10-02-2025: Code has been deployed on 7th Feb. 06-03-2025: Almost a month, not faced heap memory issue for document service so completing this point | IT | 2025-01-30
79 | RFA | RCS Issue - PID not capture properly | 1 | RCS | Defect | 59430031 and 59997960 |  | Completed | 2025-02-18 | Surendra / Ganesh / Shirish |  | 07-02-2025: Surendra to drop mail to mahesh regardint caim details 12-02-2025: Coordinate with Mahesh and get the details. Do the email follow up 18-02-2025: update the details in the code review section |  |  |  | Code changes in RCS_claim service. added full claimant name - first, middle and last.
88 |  | PHI Party Details Not Available in Claim- OC-25-2302-1005-00000036 |  | RCS | Support |  |  | Completed | 2025-02-20 | Surendra | [5 empty] | PHI detail is available in table rcs_claims.reserve_details.But isActive is false | Modified isActive status.
85 | Udyam | Udyam Seva Portal - addition details Save not working |  | RCS | Defect | 60041696 |  | Completed | 2025-02-18 | Pravin |  | 18-02-2025: Pravin to work on it Today 18-02-2025:Pravin has fixed the issue and deployed to UAT for testing and Vandna has done testing for the same and given confirmation on mail. | 2025-02-18 | Vandna | claim service, branch - latest-uat branch
56 | Surveyor Appointment | Need to allow investigator addition for Self-Workflow – ILM and Cattle scenario need to handle | 2 | Opus / RCS | CR | OP-2258 | Open | Under Development | 2025-03-28 | Pratiksha / Pravin / Ganesh |  | 05-02-2025: Pratiksha will start workin on it from tomorrow 10-02-2025: Pratiksha to drop testing mail to mahesh 11-02-2025: Call has 3 requirement and multiple validations. All can test together. No development done previously for this call from pratiksha side. 27-02-2025: old call number 59111160 05-03-2025 : Follow up with saritha and update me. Discuss the opus side change with Ganesh and get the effort 07-03-2025: Saritha has done the UI side changes 10-03-2025: Testing done, one development pending if supplier added from claimant intrested parties then payment type should be loss SMS point to be discussed with Ganesh 11-03-2025: one development pending if supplier added from claimant intrested parties then payment type should be loss SMS point to be discussed with Ganesh 12-03-2025: one development pending if supplier added from claimant intrested parties then payment type should be loss SMS point to be discussed with Ganesh | Vandna | 2025-01-15
89 |  | Claim No : OC-25-2406-410-00000010 Date of Loss :17-Feb-2025 - HIGHWAY MOVERS |  |  | Support |  |  | Completed | 2025-02-20 | Surendra / Ganesh / Shirish | [5 empty] | Opus issue - Claim not pushed due to error in Opus Scheduler API |  | Need to be fixed from OPUS side
90 |  | Claim Number OC-25-1101-1018-00001962 Date of Loss 13-Feb-2025 Insured name VARUN BEVERAGES LIMITED |  | Opus / RCS | Support |  |  | Completed | 2025-02-20 | Surendra / Ganesh / Shirish | [5 empty] | Opus issue - Claim not pushed due to error in Opus Scheduler API |  | Need to be fixed from OPUS side
91 | RCS | Policy No.OG-25-1705-4057-00000001 Claim No :OC-25-1701-4057-00000007 Date of Loss :19-Sep-2024 - M/S VIJAYSHREE AGENCIES |  | RCS | Support |  |  | Completed | 2025-02-21 | Pratiksha |  |  | Mahesh | 2025-02-21
92 |  | OC-25-2001-4094-00001238 - Wrong Defiency reason |  | RCS | Support |  |  | Completed | 2025-02-21 | Pravin |  |  | Mahesh | 2025-02-21 |  | Task Number is not updated for subject claim in rcs_claims.task_details . due to duplicate primary key error. task number is generated at the time of claim intimation. | Manually inserted new task number
93 |  | OC-25-1901-1068-00001159 ESL STEEL LIMITED - surveyor is not available on claim reserve screen to update the reserve amount |  | RCS | Support |  |  | Completed | 2025-02-24 | Surendra |  |  | Mahesh | 2025-02-24 |  | Surveyor entry in rcs_claims.reserve_details table is incomplete. missing ip_no, party_type
94 |  | Increase salvage approval Limit _Tuljaprasad Jadhav |  | RCS | Support |  |  | Completed | 2025-02-24 | Surendra |  | 24-02-2025: Configuration has ben done from backen | Vandna | 2025-02-24 |  | Production support | DB configuration done for Master data - rcs_claims.salvage_approval_master | need to provide functionality to change salvage approval amount to user
95 |  | Claims Not Pushed to RCS OC-25-1205-4092-00000165 OC-25-1205-4092-00000166 |  | RCS | Support |  |  | Completed | 2025-02-26 | Surendra / Ganesh |  |  | Mahesh | 2025-02-24 |  | Opus issue - Claim not pushed due to error in Opus Scheduler API |  | Need to be fixed from OPUS side
96 |  | OC-25-2416-4010-00000096- Unable to allocate the claim. |  | RCS | Support |  |  | Completed | 2025-02-24 | Surendra |  |  | 24-Fe-25 | Surendra |  | Task Number is not updated for subject claim in rcs_claims.task_details . due to duplicate primary key error. task number is generated at the time of claim intimation. | Manually inserted new task number
97 |  | Stake Code Empty Error Supplier Name: KARANDE ASSOCIATES Supplier ID: 452586 Partner ID: 343316188 Stake: INV |  | RCS | Support |  |  | Completed | 2025-02-25 | Surendra |  |  | Mahesh | 2025-02-25 |  | Stake code addition functionality not available to user | Manually data insert in cccp_bagic.parties table | Need to provide Stake code addition functionality to users.
98 |  | File No - 80115 ¦¦ Claim No OC-25-1101-420-00000004 ¦¦ ACID NO :- SR/604 ¦¦ Policy no :- OG-25-1113-0420-00000017-Insured :- STANFORD LABORATORIES PVT LTD--Date and time of loss :-17-01-2025 removed the earlier added supplier from OPUS as it was not showing in RCS. Now we are trying add the same supplier again but getting an error |  | RCS | Support |  |  | Completed | 2025-02-25 | Surendra |  |  | Mahesh | 2025-02-25 |  | rcs_surveyor.survey_details - surveyor was present against given surveyor category and claim Number. On removing surveyor from Opus , surveyor is not getting removed in RCS | removed old entry for surveyor
100 |  | OC-25-1201-4014-00000018 Name: GROVER ASSOCIATES Supplier ID, 8834 Partner ID, 5959754 Name and role( SUR/INV) INV |  | RCS | Support |  |  | Completed | 2025-02-25 | Surendra |  |  | Mahesh | 2025-02-25 |  | Stake code addition functionality not available to user | Manually data insert in cccp_bagic.parties table | Need to provide Stake code addition functionality to users.
102 |  | OC-25-1401-4030-00000003 - claim unable to complete the loss assessment |  | RCS | Support |  |  | Completed | 2025-02-26 | Pratiksha |  |  | Mahesh | 2025-02-26
99 |  | Unable to claim review and Surveyor appoint in RCS due to Claims not showing in RCS system, Claim Nos.OC-25-2401-1068-00002199 & OC-25-2401-1068-00002204 - Claim not pushed from opus to rcs |  | Opus | Support |  |  | Completed | 2025-02-25 | Ganesh |  | 06-03-2025: Claims are pushed on 25th Feb | Mahesh | 2025-02-25 |  | Few claims are not getting pushed from Opus to RCS | Opus issue | Need to be fixed from OPUS side
103 |  | Claim Reopen Issue - claims are being reopened in OPUS but same are not getting open in RCS |  | RCS | Support |  |  | Completed | 2025-02-27 | Ganesh / Surendra |  | 27-02-025: Surendra to update the claim staus and revert. Get the RCA from Ganesh | Mahesh | 2025-02-27 |  | OPUS: "Claim status update " API issue. On Reopening claim in OPUS , status is updated in RCS. In present case Claim is getting reopened in OPUS, but in RCS it is Closed. | Manually opened in RCS | Need to check and fix from Opus side.
104 |  | Change of Closing Reason: update the closing reason for attached claim |  |  | Support |  |  | Completed | 2025-02-24 | Surendra |  |  | Vandna | 2025-02-27 |  | User wanted to change closing reason remark for a list of closed claim numbers. closing reason changed from : "Claim Closed Due to Non submission of documents " to "Claim Closed Due to Non-Cooperation from Insured " | DB configuration done | NA - support issue
105 |  | File No 60193: Zet Town India Private Limited: Claim reported under Policy No. OG-24-1113-4008-00000105, DOL - 31-07-24 , Stock damage due to inundation PIBL No. 531785 , Claim No. OC-25-1101-4008-00000046 ¦¦ Without Prejudice' PCIS01/24-25/01297 |  |  | Support |  |  | Completed |  | Surendra / Ganesh | [5 empty] | OPUS: "Claim status update " API issue. On Reopening claim in OPUS , status is updated in RCS. In present case Claim is getting reopened in OPUS, but in RCS it is Closed. | Manually opened in RCS | Need to check and fix from Opus side.
106 |  | Claim No : OC-25-1204-4056-00000215 under policy OG-25-1204-4056-00034047 Date of Loss :14-Feb-2025 - MR ADITYA KIDS COLLECTION PROP BHUPINDER SINGH |  |  | Support |  |  | Completed |  | Surendra | [5 empty] | rcs_surveyor.survey_details - surveyor was present against given surveyor category and claim Number. On removing surveyor from Opus , surveyor is not getting removed in RCS | removed old entry for surveyor
107 |  | Reopen Main status ¦¦ (SIPL/JAN/24-25/101873) RHI Wetro damaged blocks ; Insured : Asahi India Glass Ltd ; Location : Roorkee//FILE NO 80061//claim no OC-25-1101-1015-00000014//Without prejudice |  |  | Support |  |  | Completed |  | Surendra | [5 empty] | Claim is reopened in OPUS. But same is not done in RCS. | Manually opened in RCS | Need to check and fix from Opus side.
31 |  | Allocate Screen Issue - OC-25-1901-4097-00000126 | 1 | RCS | Support |  |  | Under Monitoring | 2025-01-13 | Pratiksha / Surendra / Praveen |  | 13-01-2025: Pratiksha will check 14-01-2025: Confirm with Mahesh and complete the task | Mahesh | 2025-01-10 |  | Sub status of claim was not updated as expected. claim push was not happened properly | Updated the claims sub status Deleted the claim from RCS and repush the claim agains | Need to find | 13-01-2025: Pratiksha will check 14-01-2025: Confirm with Mahesh and complete the task
87 |  | OC-25-2203-1018-00000190 - wrong deficiency dropdown list is coming |  | RCS | Support |  |  | Under Monitoring | 2025-02-20 | Surendra / Pratiksha |  | 20-02-2025 : Case is fixed from backend, this happening because fo duplicate task id |  |  |  | Task Number is not updated for subject claim in rcs_claims.task_details . due to duplicate primary key error. task number is generated at the time of claim intimation. | Manually inserted new task number
108 |  | Claim no. OC-25-1901-1018-00002743 // NILKAMAL LTD - surveyor appointment date is coming blank |  |  | Support |  |  | Completed | 2025-03-04 | Surendra |  | 04-03-2025: Surendra is working on it | Mahesh | 2025-03-04 |  | duplicate entries in table rcs_surveyor.survey_visit_details for one surveyor_no | Manually made one entry as false
109 | ALL | RCS-Claim Service- Auth token is not passed from RCS frontend code. Issue is a part of VAPT points fro call number 59415522 |  |  | Enhancement |  |  | Development Testing | 2025-03-11 | Pratiksha |  | 05-03-2025: Frontend changes has been done, pratiksha will test it today 06-03-2025: Under Testing 10-03-2025: Facing issue at the time of allocating claim, request for payment
109 |  | UNABLE TO ADD SUPPLIER IN RCS - Getting stake code empty error |  |  | Support |  |  | Completed | 2025-03-05 | Surendra |  | 06-03-2025: Stake details are configured in the RCS system |  |  |  | Statk update issue
110 |  | #SYSTEM ERROR WHILE CLOSING THE CLAIM - facing issue in claim closing |  | RCS | Support |  |  | Under Monitoring | 2025-03-06 | Surendra |  | 07-03-2025: Claim was closed from backend so couldn't able to debugg | Mahesh | 2025-03-06
111 |  | OC-25-1901-4094-00000151 AGARWAL FOUNDRIES - supplier in not visible on claim reserve page |  | RCS | Support |  |  | Completed | 2025-03-10 | Surendra |  |  | Mahesh | 2025-03-10
112 |  | CLAIM - No : OC-25-1901-9931-00000050 Date of Loss :22-Jun-2024 - ANIRUDHA RAJENDRA KALE - Kindly update stake code. |  | RCS | Support |  |  | Completed | 2025-03-10 | Surendra |  |  | Mahesh | 2025-03-10
113 |  | FW: FCA / PCA - MIS generation with additonal fields - create the below user ids for Udyam Seva portal. |  | RCS | Support |  |  | Completed | 2025-03-10 | Surendra |  |  | Mahesh | 2025-03-10
114 |  | CLAIM - No : OC-25-1901-9931-00000050 Date of Loss :22-Jun-2024 - ANIRUDHA RAJENDRA KALE |  | RCS | Support |  |  |  | 2025-03-10 | Surendra |  |  | Mahesh | 2025-03-10
114 |  | OC-25-2202-401-00000002 - reopen subjected claim in RCS as payment rejected and claim has been reopened in OPUS |  |  | Support |  |  | Completed | 2025-03-11 | Surendra
115 |  | claim no - OC-25-2406-4056-00000036 ¦¦ Policy No. OG-24-3142-4056-00000025 ¦¦ Date of Loss: 17-Oct-2024 - STAR AUTO PROP-SITARA PRAVIN - update stake Code |  |  | Support |  |  | Completed | 2025-03-11 | Surendra
115 |  | RCS Error // Claim no. OC-25-2001-4010-00000033 - expense payment is showing in loss reserve |  |  | Support |  |  | Under Development | 2025-03-12 | Surendra / Ganesh / Rajendra |  | 12/3/2025 : Surendra, checked it was opus issue, Ganes is checking with Rajendra
116 |  | FILE NO 80127 ¦¦ CLAIM NUMBER OC-25-1101-4056-00000286 ¦¦ POLICY NUMBER OG-24-1155-4056-00018608 ¦¦ MRS VINITA MITTAL WO M L MITTAL |  |  | Support |  |  | Completed | 2025-03-12 | Surendra

## VAPT
Sr No | Application Type | Application Name | Vulnerability Title | Severity | Status On UAT/SIT/Pre-Prod | Status On PROD | Assigned To | ETA | Remark | Application Owner | Portfolio Owner | Date Of Report Submission | Closure Date | No of Days taken for Closure | Ageing Days (OPEN) | Remark
252 | Web Application | Rapid Claim Settlement | Using Components with Known Vulnerabilities | Medium | Not Tested | Open | Pratiksha |  | 10-03-2025: Can not be done | Rajendra Kumar Pradhan | Dilip Kodwani | 2024-10-01 |  |  | 139
253 | Web Application | Rapid Claim Settlement | Server Banner Disclosure | Low | Not Tested | Open |  |  |  | Rajendra Kumar Pradhan | Dilip Kodwani | 2024-10-01 |  |  | 139
254 | Web Application | Rapid Claim Settlement | Sensitive Information Disclosure | Low | Not Tested | Open | Pratiksha / Sartita |  | 10-03-2025: need to remove emai id in comment section | Rajendra Kumar Pradhan | Dilip Kodwani | 2024-10-01 |  |  | 139
255 | Web Application | Rapid Claim Settlement | Insecure HTTP Methods Are Allowed | Low | Not Tested | Open |  |  |  | Rajendra Kumar Pradhan | Dilip Kodwani | 2024-10-01 |  |  | 139
256 | Web Application | Rapid Claim Settlement | Cleartext Submission of Credentials | Low | Not Tested | Open |  |  |  | Rajendra Kumar Pradhan | Dilip Kodwani | 2024-10-01 |  |  | 139
269 | Web Application | Udyam Seva Portal | Using Components with Known Vulnerabilities | Medium | Not Tested | Open | Pratiksha |  | 10-03-2025: Bootstrap verions is updated, need to deploy and check | Rajendra Kumar Pradhan | Dilip Kodwani | 2024-10-03 |  |  | 137
270 | Web Application | Udyam Seva Portal | Insecure HTTP Methods Are Allowed | Low | Not Tested | Open |  |  |  | Rajendra Kumar Pradhan | Dilip Kodwani | 2024-10-03 |  |  | 137
271 | Web Application | Udyam Seva Portal | Cleartext Submission of Credentials | Low | Not Tested | Open |  |  |  | Rajendra Kumar Pradhan | Dilip Kodwani | 2024-10-03 |  |  | 137
296 | Web Application | Bagic Surveyor App | Open Redirection Vulnerability | Medium | Not Tested | Open |  |  |  | Rajendra Kumar Pradhan | Dilip Kodwani | 2024-10-16 |  |  | 124
297 | Web Application | Bagic Surveyor App | Cleartext Submission of Credentials | Low | Not Tested | Open |  |  |  | Rajendra Kumar Pradhan | Dilip Kodwani | 2024-10-16 |  |  | 124
298 | Web Application | Bagic Surveyor App | Missing Security Headers | Low | Not Tested | Open |  |  |  | Rajendra Kumar Pradhan | Dilip Kodwani | 2024-10-16 |  |  | 124
577 | Web Application | Udyam Seva Portal (Q4) | Vulnerable component in use | Medium | Not Tested | Open | Pratiksha |  | 10-03-2025: DO RnD and update | RajendraKumar Pradhan | Dilip Kodwani | 2025-02-12 |  |  | 5
578 | Web Application | Udyam Seva Portal (Q4) | Improper Input Validation | Low | Not Tested | Open |  |  |  | RajendraKumar Pradhan | Dilip Kodwani | 2025-02-12 |  |  | 5
579 | Web Application | Udyam Seva Portal (Q4) | Cleartext submission of credentials | Low | Not Tested | Open |  |  |  | RajendraKumar Pradhan | Dilip Kodwani | 2025-02-12 |  |  | 5
299 | Web Application | Whisleblow | Using Components with Known Vulnerabilities | Medium | Not Tested | Open | Pratiksha |  | 10-03-2025: need to update jquery from keycloak site | Rajendra Kumar Pradhan | Dilip Kodwani | 2024-10-15 |  |  | 125
300 | Web Application | Whisleblow | Expired SSL Certificate | Low | Not Tested | Open |  |  |  | Rajendra Kumar Pradhan | Dilip Kodwani | 2024-10-15 |  |  | 125

## Surendra
Task | Status | From Date |  |  |  |  | To Date | Remark | Efforts |  | From Date | To Date
New System setup due to domainId change | Completed | 2025-01-17 |  |  |  |  | 2025-01-23 | New domainId , new system and raised SR's for database access | 32 |  | 17/01/25 | 23/01/25
Approval Note is not correct in RCS. | Deployed in UAT-UAT cleared - Ready for deployment to Prod | 2025-01-29 |  |  |  |  | 2025-01-30 | #Call was already deployed in UAT - had to make changes in RCS code due to changes in request from Opus side | 8 |  | 29/01/25 | 30/01/25
Unable to Create New Partner ID in RCS | request Dto changed due to change in request from Opus | 2025-01-30 |  |  |  |  | 2025-01-30 | #call raised on 27/01/25. Assigned to me on 30 Jan. Opus request changed due to which partner details were not getting saved. made changes in RCS code and deployed in UAT | 4 |  | 30/01/25 | 31/01/25
Claim Closure // Claim no. OC-25-1901-1018-00002019 // MONDELEZ INDIA FOODS PVT LIMITED | defect raised by Mahesh. FIxed. | 2025-01-30 |  |  |  |  | 2025-01-30 | #claim closed from backend | 0.5 |  | 30/01/25 | 31/01/25
Audit Call - Loss Assessment screen - field addition and deletion for fire and Engineering product codes | Deployed in UAT after code changes | 2025-01-24 |  |  |  |  | 2025-01-27 | # code changes done in RCS UAT and deployed. some fields were removed and some added in Loss assessment screen | 8 |  | 24/01/25 | 27/01/25
Document Service - S3 Bucket Dev testing pending | Code changes done - pending UAT testing | 2025-01-28 |  |  |  |  | 2025-02-03 | # 3 new apis created for upload and download in RCS uat. uat testing going on | 10 |  | 28/01/25 | 45718
Audit Call - Loss Assessment screen - defect while doing calculations for Engineering product code | Pending | 2025-01-31 |  |  |  |  | 2025-02-03 | #pending | 4 |  | 31/01/25 | 45718
RCS - Paid amount is not coming in loss reserve screen | Completed | 2025-01-23 |  |  |  |  | 2025-01-24 | Completed and deployed on UAT | 4 |  | 23/01/25 | 24/01/25
Supplier addition issue - (sometime unable to appoint supplier) | Completed | 2025-01-22 |  |  |  |  | 2025-01-23 | Completed and deployed on UAT | 4 |  | 22/01/25 | 23/01/25
UAT testing and deployment | Completed | 2025-01-22 |  |  |  |  | 2025-01-31 | Completed | 8 |  | 22/01/25 | 31/01/25
Standup meeting and meetings with users | Completed | 2025-01-22 |  |  |  |  | 2025-01-31 | Completed | 6 |  | 22/01/25 | 31/01/25
# | Screen Name | Issue Description | Task Details | PRIORITY | Task | Effort | Status | Category | Type | Call Number | Call Status | Status | Timeline | Responsible | Efforts in Hours | Remarks | Issue Raised Date | Issue Raised By | Code Review | RCA | Corrective Action | Preventive Action | OLD Remarks
71 | Invoice Submission | FW: OC-25-1602-4056-00000051 OG-25-1603-4056-00000885 MR JACKSON KURIAN 18-Jul-24 | table : rcs_surveyor.survey_communication_details . while raising RFA, final report date is getting checked for both Surveyor and investigator. | 5 | While raising ILM Fee, getting alert as to update the final report date, this was happening to due to duplicate supplier Id | 12 hours | NA | RCS | Support | NA | NA | Completed |  | Pravin |  |  | Vandna | 20-02-2025 |  | Supplier duplicate
93 |  | OC-25-1901-1068-00001159 ESL STEEL LIMITED - surveyor is not available on claim reserve screen to update the reserve amount | Surveyor entry in rcs_claims.reserve_details table is incomplete. missing ip_no, party_type. | 4 | On Claim Reserve Screen, Surveyor details were not visible, this was happening due to incomplete surveyor details after updating the surveyor details. it is visible | 12 hours |  | RCS | Support |  |  | Completed | 2025-02-24 | Surendra |  |  | Mahesh | 2025-02-24 |  | Surveyor entry in rcs_claims.reserve_details table is incomplete. missing ip_no, party_type
96 |  | OC-25-2416-4010-00000096- Unable to allocate the claim. | DUPLICATE with 87 | 1 | Unable to allocate the claim due to wrong defiency reason | 12 hours | Done | 10-03-2025: Handled condition from backend DB, updated the latest ID is latest, so that next id will not be duplicated | Support |  |  | Completed | 2025-02-24 | Surendra |  |  | 24-Fe-25 | Surendra |  | Task Number is not updated for subject claim in rcs_claims.task_details . due to duplicate primary key error. task number is generated at the time of claim intimation. | Manually inserted new task number
106 |  | Claim No : OC-25-1204-4056-00000215 under policy OG-25-1204-4056-00034047 Date of Loss :14-Feb-2025 - MR ADITYA KIDS COLLECTION PROP BHUPINDER SINGH | Table rcs_surveyor.survey_details - surveyor was present against given surveyor category and claim Number. On removing surveyor from Opus , surveyor is not getting removed in RCS. Need to be checked from Opus side. | 3 | Surveyor Category Already Assiged - removed the supplier from the claim still getting the error while adding new supplier in RCS | 12 hours | Inprogress | 11-03-2025: Surendra will start workin on it today 12-03-2025: Surendra will start workin on it today, yesterday was working on common service issue for udyam download task | Support |  |  | Completed |  | Surendra | [5 empty] | rcs_surveyor.survey_details - surveyor was present against given surveyor category and claim Number. On removing surveyor from Opus , surveyor is not getting removed in RCS | removed old entry for surveyor
87 |  | OC-25-2203-1018-00000190 - wrong deficiency dropdown list is coming | Task Number is not updated for subject claim in rcs_claims.task_details table due to duplicate primary key error. this is due to manual insertion of entry in subject table. |  |  |  |  | RCS | Support |  |  | Under Monitoring | 2025-02-20 | Surendra / Pratiksha |  | 20-02-2025 : Case is fixed from backend, this happening because fo duplicate task id |  |  |  | Task Number is not updated for subject claim in rcs_claims.task_details . due to duplicate primary key error. task number is generated at the time of claim intimation. | Manually inserted new task number
109 |  | UNABLE TO ADD SUPPLIER IN RCS - Getting stake code empty error | Stake code update issue : DB configuration is done manually in table cccp_bagic.parties. User provides data like Supplier ID, PID,Name, Role for configuration. (Need to discuss with Mahesh - Weekly updation can be done?) | 2 | UNABLE TO ADD SUPPLIER IN RCS as stake details are not present in RCS | 12 hours | Inprogress | 11-03-2025: API develeopment done and tested locally and raised SR for API gateway configuration. Frontend integration pending 12-03-2025: SR closed, but not getting response from API, Need to drop folloe up mail to cloud team | Support |  |  | Under Development | 2025-03-05 | Surendra | [5 empty] | Statk update issue
15 * 4
|  |  | 09:30 Total Hours |  | 8 working | 4 Hour Support | 60 Hours

## Pravin
Issue | Remark | fromDate | toDate | Efforts | Status
Unable to download - on “Allocate Claim Page” unable to download the report | Changed Method implementation. Removed lazy loaded fetching of data from db and added dynamic native sql query to increase performance. Created Dto classe and method for mapping.After code review. Deployed to UAT | 2025-01-21 | 2025-01-31 | 12 Hrs | Deployed to UAT
Place of Loss and estimate amount is not coming on data entry screen from opus | Debugged and checked the data in tables since place of loss is coming from opus side provided neccessary data to Shirish to check in table whether data is present in table or not. | 2025-01-24 | 2025-01-27 | 4 Hrs | Deployed to UAT
Audit call -provided source tables for claim inbox page | provided query for fetcing required data from tables as multiple tables and joins were involved. | 2025-01-30 | 2025-01-30 | 1 Hrs | Completed
RCS- Claim Inbox search and download issue | Working on to change implementaion of method since all the data is lazy loaded and multiple conditions are involved so need to develop dyanamic query and change method implementation | 2025-01-31 | 2025-01-31 | 4 Hrs | Under Development
Policy Start date and Policy end date fields should be added in the header of each page | Worked on this CR for bringing required details in returned dto. Now deployed to UAT. | 2025-01-28 | 2025-01-28 | 4 Hrs | Deployed to UAT
Mails are not getting triggered to claim handler or to ILM responsible person in case of auto trigger or normal push/rejection. Mail format is shared in IT call. | worked on this issue check whether this issue was coming from rcs side | 2025-01-20 | 2025-01-20 | 2 Hrs | Completed
Supplier addition issue ( sometime unable to add supplier in claim, getting message as “error”) | multiple duplicate entries of suppliers mapped with unique user ids | 2025-01-23 | 2025-01-24 | 6 Hrs | Deployed
Sometime PHI does not present on reserve page. In RFA page PHI is visible but in claim reserve page and claimant interested parties pages PHI is not visible | data is not saved in RCS db when claim is intimated in opus.Temporarily fixed issue with concerned claim numbers . | 2025-01-21 | 2025-01-21 | 5 Hrs | Under Monitoring
OC-25-1101-6626-00000002 - Unable to select cause of loss for the subjected claim as dropdown is not working | Fixed the issue | 2025-01-20 | 2025-01-20 | 4 Hrs | Completed
Audit call -provided source tables for claim inbox page | provided query for fetcing required data from tables as multiple tables and joins were involved. | 2025-01-23 | 2025-01-23 | 1.5 Hrs | Completed
UAT Testing and Deployment | UAT Testing and Deployment | 2025-01-20 | 2025-01-31 | 8 Hrs | Completed
Stand Up meeting and User meeting | Stand Up meeting | 2025-01-20 | 2025-01-31 | 6Hrs | Completed
Installation of ACTIVITY TRACKER | Installation of ACTIVITY TRACKER | 2025-01-22 | 2025-01-28 | 4 Hrs | Pending

## CR Plan
# | CR Number | Description
1
2
3